## Permits
Source | Row
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Permit / licence ¦ Authority ¦ Reference ¦ Issue date ¦ Validity / expiry ¦ Status ¦ Condition notes
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Environmental Impact Decision (DIA) - PV + BESS ¦ Environmental authority (APA) ¦ DIA-2023-0147 ¦ 2023-03-10 ¦ 2027-03-10 (4 years); works must commence before expiry or decision lapses (extension possible once, 2 yrs) ¦ Issued - favourable with conditions ¦ Biodiversity monitoring 3 yrs; no works Apr-Jun in Block B (nesting)
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Production licence (generation) ¦ Energy authority (DGEG) ¦ LP-2025-0338 ¦ 2025-07-15 ¦ Until commissioning deadline 2029-06-30 ¦ Issued ¦ Includes BESS co-located
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Grid access title ¦ TSO / DGEG ¦ TA-2025-0811 ¦ 2025-06-30 ¦ Active until COD (reservation fee paid) ¦ Issued ¦ Capacity 130 MW inj / 60 MW cons
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Municipal building / civil works permit ¦ Ourique & Almodovar municipalities ¦ OP-2026-117 / AL-2026-064 ¦ 2026-05-20 ¦ 3 years ¦ Issued ¦ Archaeological watching brief condition
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Archaeology work authorisation (geophysics, trenching) ¦ Heritage authority ¦ - ¦ - ¦ - ¦ Application pending ¦ Required prior to construction
03_Permits_Licences/Permit_Tracker_SAH.xlsx | dition
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Archaeology work authorisation (geophysics, trenching) ¦ Heritage authority ¦ - ¦ - ¦ - ¦ Application pending ¦ Required prior to construction
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Water resources (stream crossings, swales) ¦ Hydrographic authority ¦ TUR-2026-0092 ¦ - ¦ - ¦ Application in review ¦ Expected Q4 2026
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Fire safety project approval (BESS) ¦ National civil protection / fire authority ¦ - ¦ - ¦ - ¦ Not yet submitted ¦ Needs LSFT evidence / spacing justification
03_Permits_Licences/Permit_Tracker_SAH.xlsx | Forest felling (cork oak) authorisation ¦ Forest authority (ICNF) ¦ AB-2025-221 ¦ 2025-10-02 ¦ 2 years ¦ Issued ¦ Compensatory planting 1:3